## Slide 1: Project Kickoff Meeting
Discovery Stage
August 17, 2021

## Slide 2
Notes: Jeff Slide

## Slide 3: Agenda
Introductions
Scope – Discovery Stage
Project Lifecycle & Approach
Project Governance & Communication
Discovery Process
Next Steps
Q & A

## Slide 4: Introductions
Great things in business are never done by one person.
They’re done by a team of people.
- Steve Jobs

## Slide 5: Nimble Team
Executive Sponsor | Daryl Stevenson General Manager, Nimble AMS Email: Daryl.Stevenson@communitybrands.com
Project Sponsor | Prassanth Lakshminarasimhan Director, Client Services Email: Prassanth.l@communitybrands.com
PMO Manager | Tina Carr, PMP Manager, Enterprise Software Project Management & Services Operations Email: Tina.carr@communitybrands.com
Development Manager | Jake Juby Development Manager Email: Jake.Juby@communitybrands.com
Customer Account Director | Julie Tracz Customer Account Director Customer Success Email: Julie.Tracz@communitybrands.com
Data Manager | Jim Zerbe Data Manager Email: Jim.zerbe@communitybrands.com
Project Manager | Phyllis Carroll, PMP, CSM Project Manager Email: Phyllis.carroll@communitybrands.com
Nimble Consultant Lead | Geoff Williams Director of Business Solutions Email: Geoff.williams@communitybrands.com
Nimble Consultant | Jeremy Thompson Nimble Consultant Email: Jeremy.thompson@communitybrands.com

## Slide 6: AFP Team
Executive Sponsor | Mike Geiger Chief Executive Officer Email: mike.geiger@afpglobal.org
Primary Project Contact / AFP Project Manager | Nicholas Ricci Director, Digital Experience Email: nicholas.ricci@afpglobal.org

## Slide 7: Contract Scope
Discovery Stage

## Slide 8: Contract Scope – Discovery (590 hours)
Terms, Conditions and Deliverables from SOW | 
Standard Modules | CRM, Committees, Accounting, Membership, Donations, Events Merchandise, Certification, Sponsorship, Advertising, Programs
Extended Config & Extensions | Sales Management/Cloud, Certification, Merchandise Special Pricing Events, Donations, Membership, CRM
Integrations | Event registration Accounting config integration Webinar integration SSO, CMS, LMS integrations AFP to implement Outlook integration AFP to work with 3rd party for e-Marketing setup, Nimble to assist
Training | Two days Familiarization - completed July 2021
Data Conversion | Data conversion orientation and planning session Support for data mapping

## Slide 9: Project Lifecycle
It’s a journey, not just a destination.

## Slide 10: Nimble AMS Project Lifecycle
Onboarding
  Nimble Team
  Transition from Sales
  Setup project site and tools
  Schedule Kickoff Meeting
  AFP Team
  Fill-out Discovery Workbooks
  Provide additional artifacts
  Attend Familiarization Training
Discovery
  Nimble Team
  Review Legacy System & Artifacts
  Document Requirements & Solutions
  Estimate scope and Cost
  Create contract modification
  AFP Team
  Attend & Engage in Discovery Sessions
  Define Data Conversion Scope
  Approve Solutions
  Create Parking Lot
Implementation
  Nimble Team
  Schedule Iterative Releases
  Configure Custom Solution (as needed)
  Address Issues & Questions
  Load Test Data
  AFP Team
  Attend Demos & Review Config
  Finalize Mapping & Validate Data
  Attend Training
  Perform User Acceptance Test
Launch
  Nimble Team
  Perform Launch Checklists
  Move System to Live
  Convert Final Data
  Support 2 weeks
  Transition to Support
  AFP Team
  Authorize Go-Live
  Provide Final Data
  Notify Members
  Attend Training
Governance: Status Reporting ● Checkpoints/Gates ● Review Schedule, Budget, Issues, Risks

## Slide 11: Project Timeline
Confirm
Review Base Features - Document Gaps
Discovery
Discovery Meetings- Requirements Capture
Launch
Transition to Support
Launch Readiness
Final Data Conversion
Implementation
Base Configurations
Extended Configurations
Extensions
Integrations
Data Conversion
Core Team Training
AFP Testing & Acceptance
Data Mapping & Test Data Conversion
Data Conversion Orientation & Estimates
Configurations & Development Iterations
Launch Support
End-User Training
End to End Testing
Project Scope & SOW
Project Signoff
Configure
Demonstrate
Test
Release
Confirm
Iterations

## Slide 12
Discovery Stage
Sign Offs
Discovery Documents
Implementation Estimates
Remote Meetings and Calls
Kickoff
Data Discovery
Discovery Sessions
Discovery Document Review
Estimate Review
Client Review and Feedback
Workbooks
Discovery Documents

## Slide 13: Project Approach: Time Commitments
AFP Time Commitment
Nimble AMS Team Time Commitment
1
Discovery
Outcome: Timeline, scope review
Go-Live
Transition staff and members to NAMS
Discovering
Scoping
Planning Config
Configure
Release Testing
End-to-End Testing
Go Live
Map and Convert
Test Data
Time Commitment
Configuration
Set up and test NAMS in iterative 2-week sprints
2
E2E Testing
End-to-End testing
prior to Go-Live
3
Transition to Support

## Slide 14: Agile is a “Nimble” Approach
The Agile movement seeks alternatives to traditional project management. Agile approaches help teams respond to unpredictability through incremental, iterative work cadences and empirical feedback.
We work in “sprints”
Tickets represent tasks
Planning is a collaboration
We honor our commitments
“WE” (your team and our team) succeed together!

## Slide 15: Nimble Philosophy
Work together
Start small
Start simple
Feedback early and often
Get people to use it
Phase in additional items

## Slide 16: Data Conversion Process
Data Discovery
  Determine the data from current “legacy” system(s) to move into Nimble AMS
Data Mapping
  Determine where to map the current data into Nimble AMS tables/fields
Conversion of Test Data
  Nimble AMS Data Team converts data that is provided by AFP Team
  AFP Team reviews Nimble AMS system and validates the data
  Rework may be needed by AFP Team to clean data and refine mapping
Conversion of Final Data
  Legacy System(s) Sunset, Final Data Delivery
  Final Data Review prior to opening system to Members

## Slide 17: Project Testing
Work divided into multiple releases: Configuration, Integrations, & Data
Nimble AMS Team demonstrates release and provides test scripts
AFP Team fully tests the release within a 5-business day period
  AFP Team reports issues through Jira
  AFP Team documents pass/fail for test cases
AFP Team signs off on release
Inadequate testing may delay any needed changes and affect subsequent releases
Functional Release Testing
Limited Scope of System Functionality
User Acceptance Testing (UAT)
after all configuration completed
and all data converted
AFP Team documents test plans
AFP Team may bring in additional Staff
AFP Team may request additional training beforehand
AFP Team Signs Off on System and Approves Launch
Inadequate testing may delay launch and result in changes in scope and post-launch issues
End to End Testing
Complete Scope of System Functionality

## Slide 18: Release Testing
PURPOSE: To test functionality that was just built.
SCOPE: Limited to current sprint
FREQUENCY: As needed after each sprint (2 weeks)
Nimble AMS holds “Showcase” to demo new functionality.
AFP fully tests that work in a timely fashion and reports issues.
Notes: Full set of original bullets:
Work divided into multiple releases: Configuration, Integrations, Data
Nimble AMS Team demonstrates release and provides test scripts
NASPP Team fully tests the release within a 5-business day period
NASPP Team reports issues through Jira
NASPP Team documents pass/fail for test cases

## Slide 19: End-to-End (E2E) Testing
PURPOSE: To test all functionality together with all converted test data
SCOPE: Entire project
FREQUENCY: Once, leading up to Go-Live
AFP tests all work in a timely fashion and reports issues.
AFP signs off on system and approves Go-Live.
Notes: Full set of original bullets:
User Acceptance Testing (UAT) after all configuration completed and all data converted
NASPP Team documents test plans
NASPP Team may bring in additional Staff
NASPP Team may request additional training beforehand
NASPP Team Signs-Off on System and Approves Launch

## Slide 20: Importance of Testing
It’s important to allow sufficient time for testing
It’s vital that key staff are engaged in testing
Develop a well-thought-out plan for End-to-End Testing to help organize the team
Put time and money into testing now and you will save time and money in the long run
Source: National Institute of Standards and Technology (NIST),
Planning Report 02-3 The Economic Impacts of Inadequate Infrastructure for Software Testing

## Slide 21: Governance & Communication Plan
The single biggest problem in communication is the illusion that it has taken place.
- George Bernard Shaw

## Slide 22: Governance Structure & Escalation Path
Escalation Path
Project Manager
Nick Ricci
Functional stakeholders + Subject Matter Experts
Project Sponsor
Prassanth Lakshminarasimh
Project Manager
Phyllis Carroll
Consulting Lead/Director
Geoff Williams
Development Manager
Jake Juby
Data Conversion Lead
Jim Zerbe
Consultant
Jeremy Thompson
Sales Account Executive
Rob Banwar
Daryl Stevenson General Manager Nimble AMS
Software
Developer(s)
Executive Sponsor
Data Specialist
Customer Success
Julie Tracz
Project Manager
Nick Ricci

## Slide 23: Communication & Governance
Communication:
  Primary Point of Contact for Nimble AMS is the Project Manager
  PM Communication Tools: Google Drive and Basecamp
  Consultants and Project Team Communication Tools: Confluence and Jira
    Document Requirements and Test Scripts
    Log and Track Issues
Governance:
  Regular status meetings
  Documented Decisions, Issues and Risks
  Tracking of Action items
  Reporting burn rate on budget
    NOTE: AFP requires hours spent be reported in one of two data categories:
      Planning
      Implementation
  Monitoring Schedule

## Slide 24: Communication Tools
Tool | Purpose | Use Frequency for AFP
 | Basecamp is an online private, secure space where teams can organize and discuss everything about a project. This essentially replaces email and allows for all communication and deliverables to be stored in one location. | High
 | Contains the project requirements in the form of epics, tasks, and stories. Manages the project deliverables. Feedback that is a direct result of testing should be logged here in the form of bug tickets. Client Licenses Limited to four per organization. | Medium
 | Contains the test suites & success guides used for testing and reference after go-live. Each AFP has their own space. Internally, Confluence is used for employee spaces and process management. | Medium
 | Google Drive provides a shared workspace for project artifacts, including contracts, requirements documentation, meeting notes, and slides. | Medium
Microsoft Project | Microsoft Project used to document project schedule and track completion of milestones. Client copies can be distributed in PDF format if/as necessary. | Medium

## Slide 25: Another Look at Project Communication
Phyllis Carroll
Project Manager is the primary point of contact
Collaboration using Google Drive and Basecamp for Project Workbooks, Discovery Documents, Status Reports and Q&A.
Weekly status calls:
Decisions, Issues and Risks
Action items
Budget burn rate reporting
Project schedule
Jira and Confluence used to document requirements, user stories, and success guides. During testing period, used to log bugs.
Microsoft Project

## Slide 26: Discovery Process
A good beginning makes a good ending!

## Slide 27: Importance of Requirements
A Good Requirement states:
  Who is Responsible
  What Shall be Done
Defines Scope, Needs, Goals, Objectives
Identifies Constraints and Dependencies
Documents Assumptions
Defines all external interfaces
States the Vision and allows for Buy-In from all Stakeholders
Tools
  User Stories

## Slide 28: What is a user story?
“As a <user profile>, I need to be able to do something so I can accomplish some goal/recognize some business benefit.”
Provides a non-technical explanation of how the system needs to be able to act from the user’s perspective
Define the expectation for the end result—”begin with the end in mind”
Explain the who, what, when, where, and why…just not the how

## Slide 29: Writing Good User Stories
Who is using this functionality?
What is the functionality that is needed?
What is the business benefit of this feature? What does it enable the user to do that they couldn’t do otherwise?
Is this story adequate to cover all aspects of what the user needs in this feature?
Am I describing what the user needs vs how I think things should be done?
Did I include enough information to lead to a design that meets my user’s needs?

## Slide 30: Sample User Stories

## Slide 31: Discovery Process
Remote Meetings
  Identify System Requirements
  Review Business processes and rules
Pre-requisites: Completed Workbooks & Familiarization Training
Lead Discussion
Document requirements
Configure Base Nimble AMS
Determine Scope of Data Conversion
Provide Solutions and LOE
Document contractual changes if needed
Nimble AMS Team
Provide business process information and artifacts
  Existing SOPs, Reports, Forms
  Legacy Applications
Answer questions and review documentation
Select work to be funded
Sign-off on scope
AFP Team

## Slide 32: How the Discovery Sessions Work
Nimble Team leads series of remote sessions
  AFP team members attend sessions relevant to them.
In each session, we use the AFP’s workbooks as a reference to discuss questions and current business processes attached to them.
We invite you to...
be collaborative
be open to changing current processes
be OK with bumping things to phase 2

## Slide 33: What to Expect During Discovery
We ask you to approach Discovery with openness and collaboration
We are working towards a common goal
We may challenge your existing practices
We will offer suggestions to streamline processes
We will provide options to avoid custom configuration
We will ask you to confirm our understanding

## Slide 34: What to Expect During Discovery
To manage scope and schedule, you may need to prioritize requirements.
Some scope may be moved to the roadmap for future phase.
Rough Order of Magnitude (ROM) provides a range of hours to help with prioritization
  Low < 10 Hours
  Medium 10-50 Hours
  Large 50-100 hours
Scope & Cost Baseline
Prioritization
Internal Reviews & Feedback Sessions
Discovery Workshop
Gap Requirements
Approved
Rough Order of Magnitude (ROM)
High-Level Technical Solution
Future Phase
Deferred / Declined
Future Phase
Implementation Phase

## Slide 35: Meeting the Go-Live Goal
Timeline
Scope
Resources
3 legs of the project management stool:
  Scope
  Timeline
  Resources
Delaying the go-live date (timeline) will impact the resources ($$)
These common events will impact both resources ($$) and timeline:
  Increasing scope
  Staff turnover
  Any sort of delays

## Slide 36: Next Steps

## Slide 37: Next Steps
Complete Workbooks & Deliver to Geoff Williams
  Due no later August 30th (sooner = better)
Schedule Discovery Q&A Sessions – Geoff Williams
Schedule Kickoff Data Discovery Session –Jim Zerbe
Schedule Weekly Status Meetings – Phyllis Carroll
Document Blackout Periods in Schedule – Phyllis Carroll (AFP input)
Allow Staff Time for Discovery – AFP Management